## Sheet1
Date | Editor | Commit Comment | Description of Updates | QA/QC Testing Procedure | Editor QC | Non-Editor QC | ID | Version
2015-09-18 | Adam Brez | removed renderers. Applied symbology to services | opened each feature service/overlay within an AGO webmap and symbolized the layer to be the same as the renderer within the SPM. The feature layer was saved and the renderer/symbology javascript was deleted from the application. | View each overlay within the current production SPM alongside the current working version of the SPM. Compare the symbology statewide and in 3 specific, zoomed in locations to verify the save symbology matches the rendered symbology. | YES | YES | 45 | 4.1.1 info
2015-09-22 | Adam Brez | moved all functions and events into dojo framework | moved all javascript/functions within the primary dojo mapping function. Created script events within the primary dojo function for each event previously attributed to the html objects. Deleted the html inherent events. | Test every button and functionality within the application | YES | YES |  | 4.1.1 info
2015-09-22 | Adam Brez | updated DOJO parameters | deleted the extension call for each dojo widget/dijit and replaced them with their shortened dojo parameter |  | YES | YES |  | 4.1.1 info
2015-09-22 | Adam Brez | measure & sketch tools fixed | botht eh measure tool and the sketch tool permitted drawing multiple polyline segments and actually included the distances between them when calculating the total measured distance and DE project distance. Added a variable to hold each segment length for the DE tool, set the measure tool to refresh measuring the distance with each line drawn, and created a 'mouse-move' event so that the measured distance fluvially updates with mouse movement. | Make multiple segments with each unit type in the Measure tab. DO this both in the current version and this working version of the SPM and compare. Repeat this process in the Sketch Tool tab, making a project with multiple segments very far away from each other to ensure that the total project length doesn't include the gap between the segments | YES | YES |  | 4.1.1 info
2015-09-23 | Adam Brez | fixed cursor/pointer issues | the application had a blanket CSS for all table of contents DIVs to have a pointer when the cursor was moved overtop them regardless if the object was clickable or not. I have adjusted the CSS to show a pointer only when the cursor hovers over clickable objects (overlays, buttons, radio buttons, etc.) | for each tab in the TOC hover the pointer over all objects and verify that the pointer hand shows up for clickable objects and also does not show up for non-clickabl objects | YES | YES |  | 4.1.1 info
2015-11-16 | cbardash | fixed Railroad legend/fixed Area Office misspelling/added link to minute orders | Fixed Railroad Legend and Popup to show text descriptions instead of codes. Replaced railroad service with new service. Replaced InfoTemplate with PopupTemplate, since InfoTemplates cannot interpret coded domain values. Changed Area Office layer to point to new service. Added District Name to the popup window. Added a link in the popup for the Highway Designation layer that points to the Minute Orders page based on the minute order number in the popup. | see SPM_TestScrip.docx | YES | YES | 44, 43, 41 | 4.1.1 info
2015-11-17 | cbardash | added area office renderer/fixed RR popup title/ removed ESRI logo | Added renderer to Area Office layer to mimic transparency on old layer Fixed RR popup title removed ESRI logo | see SPM_TestScrip.docx | YES | YES |  | 4.1.1 info
2015-12-01 | cbardash | fixed legend for Clear Overlays/updated MPO layer/updatedHighwayDesignations layer/added highlighter for Search tab | Fixed "Clear Overlays" legend. Added new 2015 MPO Map Service layer and added renderer to handle transparency problem. Replaced old service layer for Highway Designations with new Map Service (now includes historic minute orders and has been resymbolized). Added highlight function to Search tab. | see SPM_TestScrip.docx | YES | YES | 52, 40, 37, 20 | 4.1.1 info
2015-12-14 | cbardash | added survey/removed attribution from lower right-hand corner/removed ArcGIS Server layer URLs/added version number | Added survey popup screen on startup, and also survey button at bottom of TOC. Removed esriAttribution from lower right-hand corner. Switched ArcGIS Server-based services over to AGO-hosted services. Added version number to About tab. Added Jump to Google/Bing button. | see SPM_TestScrip.docx | YES | YES | 50, 27 | 4.1.1 info
2016-01-06 | cbardash | multiple fixes following updates | Multiple fixes following updates: Measure Tab: Fixed problem with other units of measure not populating. Also, first graphic clears now after starting a second. Search Tab: Changed the styling of the search results div so that it is only there if there is a result, and then it is only as big as the results. Moved clear button to map below zoom toggle. New button shows up under zoom toggle when a feature is selected. The button disappears again when clicked. Button is visible on all tabs until the highlighted feature is cleared, so that user doesn’t have to return to Search tab to clear it. Changed search results message from "Nothing found, Try a new search" to "Searching." Fixed credits at bottom right of map pane so that long credits do not show up. Disabled Esri-based credentials and hard-coded credentials to a new div. Popups hide when a new Tab or Overlay is selected. Query Tab: Comma or letter (anything other than a number) in Value field causes query to run forever. Changed field type to “number. Explanation of Control Section colors in legend. Now reads “Control Section Segment colors only serve to distinguish one segment from the next.” Repositioned Jump To button and tweak styling to round bottom edge of dropdown. Legislative boundary layers: Plan Name field in popup dialog box is always empty. Field is blank in all three service layers. Removed field from popup. Changed Maintenance Section label in legend to "Maintenance Offices" to be consistant with Overlay title. Changed Minute Order Designations title in Legend to Highway Designations to be consistant with Overlay title. | Testers from this round of major updates all tested these fixes. | YES | YES |  | 4.1.1 info
2016-02-09 | cbardash | Added meta tag to fix IR problem / Updated Maint Sec layer / added Creative Commones license | Meta tag fixes compatibility view problem with IE. Added new Maintenance Section layer on AGO and updated service. Added Creative Commons license statement to top. | Open in IE with Compatibility View turned on and check that the app looks correct and all functions work. Turn on Maintenance Section layer and select polygons to test popup. | YES | No |  | 4.1.1 info
Added Top 100 Layer with search functionality Updated AADT Layer to add 2014 AADT Updated the ESRI javascript API to 4.16 - this allowed for adding halos around labels - required an update to the search functionality Updated the Future Traffic and Freight Percentage layer Added the UZA Layer as a layer that turns on with FC and Texas Trunk at certain zoom levels Changed the color of Reference Marker Labels and added halos Added halos to AADT labels Added a new line in the popup window for FC Linework to show the Rural Code Description